## Preparation
WORKCAMP CHECKLIST
September | Pick a date for the Sign up Meeting and Schedule
Update the Website with new WC dates and Sign up Mtg Date
October | Send in date request after paperwork arrives
Reserve Church and Gym for Rehearsal and Mass after date is confirmed
November | Order Confirmation Gifts
Arrange for a Photographer
Order paper products for programs
Order confirmation robes (Red or white)
December | Send out sign-up genius
Send in completed Litrugy Form to the diocese (t.nguyen@arlingtondiocese.org)
Ask for readings from Father
Request Music from Music Director (Must send readings first)
Request Servers (5: one cross bearer, two acolytes, one miter bearer, and one crozier bearer)
Request Eucharistic Ministers
Order Cake
Send out email to parents with dates/times, other logistics
Send out photographer forms via backpack mail, email and CCD class
Request Volunteer Readers (2: 8th grade catechists)
Request one to read the Prayers of the Faithful (confirmandi may do this)
Requestion Knights of Columbus
Request Ushers
Request volunteer to help with organizing the line for photographs with the bishop
Get the check cut for the Bishop and MC
January | Send in set-up form to Larry
Confirm Readers - Include pew for them
Ask Father for priest attendance
Send Confirmandi names to the school for spell check
Gift bearers chosen
February | Wrap Confirmation Gifts
Send program sample to school for approval
Complete and fold programs
Come up with a day-of plan for rehearsal and Confirmation day
Come up with a to-do plan for RE staff for day-of; Review checklist
Resend email to parents with dates/times, other logistics
Make Certificates and get them to Father for Signatures
March | Set up seating chart alphabetically, make color-coordinated, numbered (and row) name cards for seats (2 sets: church and gym)
Send rehearsal reminder to parents
April | Send reminder to Sign up Genius volunteers (Adult volutneers when underaged volunteers are involved)
Buy flowers for decroation/gifts for teachers
Set up place for Bishop to take pictures (Backdrop, Line, chair, water pitcher)
make sure that we have volunteers to assist with robe return
May | Send reminder to Sign up Genius volunteers (Adult volutneers when underaged volunteers are involved)
Buy flowers for decroation/gifts for teachers
Set up place for Bishop to take pictures (Backdrop, Line, chair, water pitcher)
make sure that we have volunteers to assist with robe return
June | Send reminder to Sign up Genius volunteers (Adult volutneers when underaged volunteers are involved)
Buy flowers for decroation/gifts for teachers
Set up place for Bishop to take pictures (Backdrop, Line, chair, water pitcher)
make sure that we have volunteers to assist with robe return
July | Send reminder to Sign up Genius volunteers (Adult volutneers when underaged volunteers are involved)
Buy flowers for decroation/gifts for teachers
Set up place for Bishop to take pictures (Backdrop, Line, chair, water pitcher)
make sure that we have volunteers to assist with robe return

## Rehearsal
Rehearsal
Set up gym with two rows of chairs facing each other
Place name cards on chairs in gym
Have kids sit the correct chair
Correct any seating mistakes (classmates seated next to each other, rowdy kids separated, etc.)
Set up church with placecards on pews
Have photography forms available for parents in the gym
Set up to the gym microphone
Have the church microphone ready
Have photographer present
Have usher present
Have Confirmandi stand one at a time with their sponsors when coming up to be confirmed
People Needed:
2 | Two leaders for each row to lead up kids up to the church (separating at the lawn and meeting up at the church)
1 | Stagger the kids entering into the Church
6 | Teachers/catechists to sit in the pews with the kids
1 | Someone to grab the kids for bearing the gifts
2 | Door holders for School
2 | Door holders for Church

## Mass and Reception
Mass Preparation
Reserve pews for readers and their family
Reserve pew for photographer
Have the offerings out in the back of the church
Make an annoucement: No flash photography, stay in your seats, etc.
Have ribbons reserving Confirmandi and sponsor pews
Bring the programs up to the church and set the kids up
Volunteers keeping the doors open
Reception Preparation
Cut cake
Photography forms with pens
Gifts set out
Lemonade and water pitchers set out
Napkins, tablecloths, forks, plates, cups set out
set up area for Bishop pictures
set up area for robe return